## Week One
Week 1
Unstarted
Started | Daily Goal |  | Comments
Tabled
Dropped | Goals For Day 3 | Get Ben and Dan aproved Client | Get Preliminary UI up and Running | Have functional Word selection | Prepare for presentation
PROBLEM
Could Be better
DONE | Week 1 Day 1 |  |  | Week 1 Day 2 |  |  | Week 1 Day 3 |  |  | Week 1 Day 4 |  |  | Week 1 Day 5 |  |  | Week 1 Day 6 |  |  | Week 1 Day 7
Comand alt shift 2 for new row | TODO | Comments | Learned | TODO | Comments | Learned | TODO | Comments | Learned | TODO | Comments | Learned | TODO | Comments | Learned | TODO | Comments | Learned | TODO | Comments | Learned
Khayyon | Make Github | Name of Repo is Tungsten | N/A
| Set up Directory | W/ Miguel | Each directory needs a README
| Outline of frontend | W/ Miguel
Setting up Blank app
Miguel | GroupMe | N/A | N/A | Create a minimal mock UI for the suggestions | /W Khayyon | Need to consider using tests | Find a testing framework | Using Jasmine stand-alone application
| Rough Sketch of Project | [5 empty] | Refactor and clean up the code
| Outline of FrontEnd | w/K |  |  |  |  | Create some tests
Setting up Blank app
Mishig | Find Competitors
Finding Tenserflow Backend
Nicole | Write Client Model
Update Client Descriptions
get Tenser Flow Word Selection up and Running
Get Tenserflow functional on computer
Russell | Create Google Sheet | Improve Macros |  | Get JS levenshtein up and running |  |  | Finish Trie Nearest Node | Need to Solve how to get the next nearest Neightbor for things that don't end.
| Update Client Descriptions |  |  | Get JS Fast levenshtein up and running | Updated To Import Fast LevenStein |  | Start presentation Preparedness
| Get Tensert Flow Word Selection up and running |  |  | Get modules Up and Running For Nicole
Get Tenser Flow Downloaded on computer
Get Markov Chain individual guess up and Running
Get JS levenstine Shortest Distance up and Running

## SheetTODO
Write macro for Adding another line
Write Macro for Sharing TODO with another person

## Template
| TODO | Comments | Learned 1 thing
Khayyon
Miguel
Mishig
Nicole
Russell
Everyone